## RUCO 2.38
RUCO 2.38 PTY Project Details
Answer to RUCO Question : | b | c | d |  | f | i |  |  | g | h
Utility Account | Project | Project Desc | Construction Start Date | Completion Date | Replacing Existing Plant? | AIAC | CIAC | General Funding | Total Actuals as of SEP-26 | Estimated Completion Costs as of SEP-26
374 - Land and Land Rights | 250010A | Dist Land Rghts Conv O&M to Capx-Fa | 2024-07-18 | 2026-10-31 | REPLACE | N | N | Y | 134534 | -5210
376 - Mains | 251100A | Mains - Blanket - Flag | 2026-08-25 | 2026-09-04 | REPLACE | Y | Y | Y | 166850 | 81918
376 - Mains | 251101R | Mains - Blkt Refunds - Flag | 2026-07-01 | 2026-12-31 | INSTALL | Y | N | N | -25820 | 1023
376 - Mains | 251500B | PI Mains - Flagstaff | 2026-09-01 | 2026-12-31 | REPLACE | Y | Y | Y | 0 | 204223
376 - Mains | 252100A | Mains - Blanket - King | 2026-02-12 | 2026-12-31 | REPLACE | Y | Y | Y | 185730 | 66743
376 - Mains | 252101R | Mains - Blkt Refunds - King | 2026-07-01 | 2026-12-31 | INSTALL | Y | N | N | -4557 | -12293
376 - Mains | 252400S | Mains-System Improv-King | 2026-06-12 | 2026-12-31 | REPLACE | N | N | Y | 13234 | 86766
376 - Mains | 252406S | Mains PVC Replacement KNG | 2025-09-01 | 2026-12-31 | REPLACE | N | N | Y | 170426 | 225574
376 - Mains | 252500B | PI Mains - Kingman | 2026-02-01 | 2026-12-31 | REPLACE | Y | N | Y | 1 | 24626
376 - Mains | 253100A | Mains - Blanket - Pres | 2025-08-05 | 2026-09-25 | REPLACE | Y | Y | Y | 445029 | -30485
376 - Mains | 253101R | Mains - Blkt Refunds - Pres | 2026-07-01 | 2026-12-31 | INSTALL | Y | N | N | -243078 | 184686
376 - Mains | 253500B | PI Mains - Prescott | 2026-03-01 | 2026-12-31 | REPLACE | N | Y | Y | 244664 | 378801
376 - Mains | 255100A | Mains - Blanket - Verde | 2025-07-01 | 2026-12-31 | REPLACE | Y | Y | Y | 738 | 75301
376 - Mains | 255101R | Mains - Blkt Refunds- Verde | 2026-09-01 | 2026-12-31 | INSTALL | Y | N | N | 0 | -571
376 - Mains | 256100A | Mains - Blanket - Nog | 2026-02-01 | 2026-12-31 | REPLACE | Y | Y | Y | 21248 | 164264
376 - Mains | 256101A | Valve Replacement Nogales | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 30793
376 - Mains | 257100A | Mains - Blanket - SL | 2026-07-23 | 2026-12-31 | REPLACE | Y | Y | Y | 43514 | 63556
376 - Mains | 257101R | Mains - Blanket Refunds - SL | 2026-07-01 | 2026-12-31 | INSTALL | Y | N | N | -2354 | -7715
376 - Mains | 251400S | Mains-System Improv-Flag | 2026-09-01 | 2026-12-31 | INSTALL | N | Y | Y | 0 | 27941
376 - Mains | 257400S | Mains-System Improv-Show Low | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 25236
376 - Mains | 257500B | PI Mains - Showlow | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 49115
376 - Mains | 252404S | Main & Services PVC Repl KNG | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 117321 | 2679
376 - Mains | 252501B | PI Mains - Lake Havasu | 2026-09-01 | 2026-12-31 | REPLACE | N | Y | Y | 0 | 24753
376 - Mains | 253376B | Mains Volun Repl - Pres | 2025-08-05 | 2026-09-28 | REPLACE | N | N | Y | 16951 | 21156
376 - Mains | 253400S | Mains-System Improv-Pres | 2026-07-02 | 2026-12-31 | REPLACE | N | N | Y | 3599 | 39707
376 - Mains | 255500B | PI Mains - Verde | 2026-09-01 | 2026-12-31 | REPLACE | N | Y | Y | 0 | 34777
378 - Measuring and Regulating Station Equipment-Gen | 251378A | Meas&Reg Sta Distribution-Flag | 2026-09-01 | 2026-12-31 | REPLACE | N | Y | Y | 0 | 55728
378 - Measuring and Regulating Station Equipment-Gen | 252378A | Meas&Reg Sta Distribution-King | 2026-02-01 | 2026-12-31 | REPLACE | Y | N | Y | 0 | 97181
378 - Measuring and Regulating Station Equipment-Gen | 253378A | Meas&Reg Sta Distribution-Pres | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 4393 | 30883
378 - Measuring and Regulating Station Equipment-Gen | 255378A | Meas&Reg Sta DistributionVerde | 2026-04-01 | 2026-12-31 | REPLACE | Y | Y | Y | -3714 | 12028
378 - Measuring and Regulating Station Equipment-Gen | 256378A | Meas&Reg Sta Distribution-Nog | 2026-09-01 | 2026-12-31 | REPLACE | N | Y | Y | 0 | 114972
378 - Measuring and Regulating Station Equipment-Gen | 257378A | Meas & Reg Sta Eq Gen- Bl-SL | 2026-03-16 | 2026-12-31 | REPLACE | N | N | Y | 2770 | 8738
378 - Measuring and Regulating Station Equipment-Gen | 253379A | Meas & Reg Sta Eq Gen-BI-Pres | 2023-10-06 | 2026-12-31 | REPLACE | N | N | Y | 114190 | 0
379 - Measuring and Regulating Station Equipment-City | 256379A | Meas & Reg Sta Eq Gen-BI-Nog | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 2904
379 - Measuring and Regulating Station Equipment-City | 257379A | Meas & Reg Sta Eq Gen-FI-SL | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 44813
380 - Services | 251380R | Service Repl - Flag | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | -5636 | 34263
380 - Services | 252380R | Service Repl - King | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 12943 | 44171
380 - Services | 252402S | Drisco Pipe Replacement | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 605079 | 148153
380 - Services | 253380B | PI Services Repl - Prescott | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 4991 | 1315
380 - Services | 253380C | PI Service Repl - Prescott Val | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | -77 | 1675
380 - Services | 253380R | Service Repl - Pres | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 47649 | 54432
380 - Services | 255380R | Service Repl - Verde | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | -10386 | 26559
380 - Services | 256380R | Service Repl - Santa Cruz | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 355 | 26059
380 - Services | 257380R | Service Repl - Show Low | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 13672 | 20107
381 - Meters | 251381A | Meters - Bl - Flag | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 2938 | 18714
381 - Meters | 252381A | Meters - Bl - King | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 9558 | 22662
381 - Meters | 253381A | Meters - Bl - Pres | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 1477947
381 - Meters | 255381A | Meters - Bl - Verde | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 3002 | 10599
381 - Meters | 256381A | Meters - Bl - Nog | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 12119 | -4793
381 - Meters | 257381A | Meters - Bl - SL | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 14778
382 - Meter Installations | 251382A | Meter Installations - Bl -Flag | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 19054 | 82813
382 - Meter Installations | 252382A | Meter Installations -Bl - King | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 22322 | 70070
382 - Meter Installations | 253382A | Meter Installations -Bl - Pres | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 26005 | 108179
382 - Meter Installations | 255382A | Meter Installations-Bl - Verde | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 10938 | 41425
382 - Meter Installations | 256382A | Meter Installations - Bl - Nog | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 3644 | 12896
382 - Meter Installations | 257382A | Meter Installations - Bl -SL | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 17279 | 17787
383 - House Regulators | 251383A | Regulators - Blanket - Flag | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 5056 | 12987
383 - House Regulators | 252383A | Regulators - Blanket - King | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 9206 | 16570
383 - House Regulators | 253383A | Regulators - Blanket - Pres | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 14260 | 21356
383 - House Regulators | 255383A | Regulators - Blanket - Verde | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 2045 | 7621
383 - House Regulators | 256383A | Regulators - Blanket - Nog | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 778 | 1458
383 - House Regulators | 257383A | Regulators - Blanket - SL | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 3962 | 2379
384 - House Regulatory Installations | 251384A | Regulator Install - Bl - Flag | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 320 | 13456
384 - House Regulatory Installations | 252384A | Regulator Install - Bl - King | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 2605 | 16920
384 - House Regulatory Installations | 253384A | Regulator Install - Bl - Pres | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 5906 | 32929
384 - House Regulatory Installations | 255384A | Regulator Install- Bl - Verde | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 3851 | 14130
384 - House Regulatory Installations | 257384A | Regulator Install - Bl - SL | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 6007 | 3521
384 - House Regulatory Installations | 256384A | Regulator Install - Bl - Nog | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 1434 | -959
385 - Industrial Measuring Regulating Station Equipment | 251385A | Industrial Metering - Flag | 2026-07-01 | 2026-12-31 | REPLACE | N | Y | Y | 33440 | -920
385 - Industrial Measuring Regulating Station Equipment | 253385A | Industrial Metering - Pres | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 3786 | 42538
385 - Industrial Measuring Regulating Station Equipment | 255385A | Industrial Metering - Verde | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 16369
385 - Industrial Measuring Regulating Station Equipment | 257385A | Industrial Metering-Show Low | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 17328
385 - Industrial Measuring Regulating Station Equipment | 252385A | Ind Meas & Reg Sta Eq-Bl- King | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 2622 | 12020
387 - Other Equipment | 252387A | Other Distr Eq CP-Bl - King | 2026-07-01 | 2026-12-31 | INSTALL | N | Y | Y | 62669 | -1318
387 - Other Equipment | 251387A | Other Distr Equip CP-Bl - Flag | 2026-07-01 | 2026-12-31 | INSTALL | N | Y | Y | -640 | 10837
387 - Other Equipment | 255387A | Other Distr Eq CP - Bl - Verde | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 1786 | 1688
387 - Other Equipment | 253387A | Other Distr Equip CP-Bl-Pres | 2026-07-01 | 2026-12-31 | REPLACE | N | N | Y | 14574 | 1508
387 - Other Equipment | 256387A | Other Distr Eq CP - Bl - Nog | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 29551 | -4707
387 - Other Equipment | 257387A | Other Distr Equip CP-Bl - SL | 2026-07-01 | 2026-12-31 | INSTALL | N | Y | Y | 21263 | 26109
390 - Structures and Improvements | 253900A | Struct & Improv - New (Pres) | 2025-08-12 | 2026-12-31 | REPLACE | N | N | Y | 28635 | 48825
390 - Structures and Improvements | 255900A | Struct & Improv- New (Verde) | 2026-09-01 | 2026-12-31 | REPLACE | N | N | Y | 0 | 26414
390 - Structures and Improvements | 253901A | UNSG Training Facility | 2025-11-05 | 2026-10-01 | INSTALL | N | N | Y | 95200 | -4952
390 - Structures and Improvements | 257900A | Structures & Improv-New SL | 2026-05-01 | 2026-08-31 | REPLACE | N | N | Y | 5679 | 0
391 - Office Furniture and Equipment | 250912A | Comp Equip - UNSG | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 24021 | 25697
391 - Office Furniture and Equipment | 250916A | Network IT Equip - UNSG | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 32000
391 - Office Furniture and Equipment | 250917A | Systems IT Equip - UNSG | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 71281 | -45272
391 - Office Furniture and Equipment | 252910A | Office Furn & Equip-New (King) | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 25471 | 4589
391 - Office Furniture and Equipment | 253910A | Office Furn & Eq - New (Pres) | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 3750
392 - Transportation Equipment | 250000A | UNSG Transportation Equip | 2024-04-02 | 2026-12-31 | INSTALL | N | N | Y | 765239 | -110441
394 - Tool, Shop, and Garage Equip | 250940A | Tools,Shop,Gar Eq - New | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 15210 | 2540
394 - Tool, Shop, and Garage Equip | 251940A | Tools,Shop,Gar Eq-New(Flag) | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 7000
394 - Tool, Shop, and Garage Equip | 252940A | Tool,Shop,Gar Eq-New (King) | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 11302 | 17498
394 - Tool, Shop, and Garage Equip | 253940A | Tools,Shop,Gar Eq-New (Pres) | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 35424 | 180
394 - Tool, Shop, and Garage Equip | 256940A | Tools,Shop,Gar Eq-New (Nog) | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 15000
394 - Tool, Shop, and Garage Equip | 257940A | Tools,Shop,Gar Eq - New SL | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 22780 | 17220
397 - Communication Equipment | 250970A | Comm Equip - New | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 466434
397 - Communication Equipment | 257970A | Comm Equip- New SL | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 9460
397 - Communication Equipment | 250973A | UNSG Fixed Network Replacement | 2026-05-13 | 2026-12-31 | REPLACE | N | N | Y | 342079 | 1529396
397 - Communication Equipment | 251970A | Comm Equip - New (Flag) | 2026-07-01 | 2026-12-31 | INSTALL | N | N | Y | 920 | 2117
397 - Communication Equipment | 253970A | Comm Equip - New (Pres) | 2026-06-04 | 2026-09-30 | INSTALL | N | N | Y | 787 | 2281
397 - Communication Equipment | 255970A | Comm Equip - New (Verde) | 2026-09-01 | 2026-12-31 | INSTALL | N | N | Y | 0 | 1381
[9 empty] | 3869627 | 6669359
[9 empty] | Ties to Rate Base - Post Test Year Plant Proforma | 10538986