## STF 2.12
STF 2.12 PTYP_CWIP
Answer to STF Question :
h, j. | a. |  | k | f. | g, l. |  | b. | c. | e. | m. | n. | i.
Utility Account | Project | Project Description | Actuals as of Jun 30,2025 | Actuals as of Jun 30,2026 | Actuals as of Sep 30, 2026 | Estimated Completion Costs as of Sep 30, 2026 | Construction Start Date | Completion Date | Action Indicator | AIAC | CIAC | General Funding
374 - Land and Land Rights | 250010A | Dist Land Rghts Conv O&M to Capx-Fa |  | 129324 | 254720 | -125396 | 2026-08-01 | 12/01/2026 | REPLACE |  | 0 | Y
376 - Mains | 251100A | Mains - Blanket - Flag |  | 137331 | 197595 | 51173 | 2026-08-01 | 10/15/2026 | REPLACE |  | -1337.65 | Y
376 - Mains | 251101R | Mains - Blkt Refunds - Flag |  | 0 | -25820 | 1023 | 2026-07-01 | 2026-12-31 | INSTALL | -25820 | 0 | N
376 - Mains | 251500B | PI Mains - Flagstaff |  | 0 | 0 | 204223 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 252100A | Mains - Blanket - King |  | 70325 | 313270 | -60797 | 2026-10-01 | 12/31/2026 | REPLACE |  | 0 | Y
376 - Mains | 252101R | Mains - Blkt Refunds - King |  | 0 | -12972 | -3878 | 2026-07-01 | 2026-12-31 | INSTALL | -12972 | 0 | N
376 - Mains | 252400S | Mains-System Improv-King |  | 5559 | 13474 | 86526 | 2026-10-01 | 12/31/2026 | REPLACE |  | 0 | Y
376 - Mains | 252406S | Mains PVC Replacement KNG |  | 81144 | 194585 | 201415 | 2026-06-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 252500B | PI Mains - Kingman |  | 1300 | 2577 | 22050 | 2026-06-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 253100A | Mains - Blanket - Pres |  | 70636 | 536697 | -122153 | 2026-09-01 | 12/28/2026 | REPLACE |  | 0 | Y
376 - Mains | 253101R | Mains - Blkt Refunds - Pres |  | 0 | -422337 | 363945 | 2026-07-01 | 2026-12-31 | INSTALL | -422337 | 0 | N
376 - Mains | 253500B | PI Mains - Prescott |  | 219595 | 271334 | 352131 | 2026-09-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 255100A | Mains - Blanket - Verde |  | 0 | 2852 | 73187 | 2026-08-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 255101R | Mains - Blkt Refunds- Verde |  | 0 | 0 | -571 | 2026-10-01 | 2026-12-31 | INSTALL | 0 | 0 | N
376 - Mains | 256100A | Mains - Blanket - Nog |  | 1769 | 21248 | 164264 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 256101A | Valve Replacement Nogales |  | 0 | 124 | 30669 | 2026-09-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 257100A | Mains - Blanket - SL |  | 2031 | 87871 | 19199 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 257101R | Mains - Blanket Refunds - SL |  | 0 | -4962 | -5107 | 2026-07-01 | 2026-12-31 | INSTALL | -4962 | 0 | N
376 - Mains | 251400S | Mains-System Improv-Flag |  | 0 | 0 | 27941 | 2026-10-01 | 2026-12-31 | INSTALL |  | 0 | Y
376 - Mains | 257400S | Mains-System Improv-Show Low |  | 0 | 0 | 25236 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 257500B | PI Mains - Showlow |  | 0 | 0 | 49115 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 252404S | Main & Services PVC Repl KNG |  | 6126 | 198003 | -78003 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 252501B | PI Mains - Lake Havasu |  | 0 | 0 | 24753 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 253376B | Mains Volun Repl - Pres |  | 16951 | 16951 | 21156 | 2025-08-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 253400S | Mains-System Improv-Pres |  | 0 | 20784 | 22522 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
376 - Mains | 255500B | PI Mains - Verde |  | 0 | 0 | 34777 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 251378A | Meas&Reg Sta Distribution-Flag |  | 0 | 0 | 55728 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 252378A | Meas&Reg Sta Distribution-King |  | 0 | 568 | 96613 | 2026-07-01 | 11/30/2026 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 253378A | Meas&Reg Sta Distribution-Pres |  | 0 | 4697 | 30579 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 255378A | Meas&Reg Sta DistributionVerde |  | -3714 | -3714 | 12028 | 2026-04-01 | 2026-12-31 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 256378A | Meas&Reg Sta Distribution-Nog |  | 0 | 0 | 114972 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 257378A | Meas & Reg Sta Eq Gen- Bl-SL |  | 2770 | 2770 | 8738 | 2026-03-01 | 11/20/2026 | REPLACE |  | 0 | Y
378 - Measuring and Regulating Station Equipment-Gen | 253379A | Meas & Reg Sta Eq Gen-BI-Pres | 114190 | 114190 | 114190 | 0 | 2024-06-05 | 2026-12-31 | REPLACE |  | 0 | Y
379 - Measuring and Regulating Station Equipment-City | 256379A | Meas & Reg Sta Eq Gen-BI-Nog |  | 0 | 0 | 2904 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
379 - Measuring and Regulating Station Equipment-City | 257379A | Meas & Reg Sta Eq Gen-FI-SL |  | 0 | 0 | 44813 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
380 - Services | 251380R | Service Repl - Flag |  | 1058 | -6513 | 35140 | 2026-07-01 | 2026-12-31 | REPLACE |  | -10594.86 | Y
380 - Services | 252380R | Service Repl - King |  | 8232 | 45336 | 11778 | 2026-07-01 | 2026-12-31 | REPLACE |  | -15988.78 | Y
380 - Services | 252402S | Drisco Pipe Replacement |  | 107812 | 747845 | 5387 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
380 - Services | 253380B | PI Services Repl - Prescott |  | 0 | 4991 | 1315 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
380 - Services | 253380C | PI Service Repl - Prescott Val |  | 216 | 88 | 1510 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
380 - Services | 253380R | Service Repl - Pres |  | 5628 | 141005 | -38924 | 2026-07-01 | 2026-12-31 | REPLACE |  | -1540.13 | Y
380 - Services | 255380R | Service Repl - Verde |  | 990 | -6437 | 22610 | 2026-07-01 | 2026-12-31 | REPLACE |  | -8035.04 | Y
380 - Services | 256380R | Service Repl - Santa Cruz |  | 2088 | 17607 | 8807 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
380 - Services | 257380R | Service Repl - Show Low |  | 1341 | 34853 | -1074 | 2026-07-01 | 2026-12-31 | REPLACE |  | -1678.26 | Y
381 - Meters | 251381A | Meters - Bl - Flag |  | 0 | 11601 | 10051 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
381 - Meters | 252381A | Meters - Bl - King |  | 0 | 9558 | 22662 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
381 - Meters | 253381A | Meters - Bl - Pres |  | 0 | 883 | 1477064 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
381 - Meters | 255381A | Meters - Bl - Verde |  | 0 | 6003 | 7598 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
381 - Meters | 256381A | Meters - Bl - Nog |  | 0 | 32246 | -24920 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
381 - Meters | 257381A | Meters - Bl - SL |  | 0 | 2938 | 11840 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 251382A | Meter Installations - Bl -Flag |  | 3764 | 43065 | 58802 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 252382A | Meter Installations -Bl - King |  | 3248 | 38110 | 54282 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 253382A | Meter Installations -Bl - Pres |  | 2796 | 42231 | 91953 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 255382A | Meter Installations-Bl - Verde |  | 2289 | 21204 | 31159 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 256382A | Meter Installations - Bl - Nog |  | 2201 | 8082 | 8458 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
382 - Meter Installations | 257382A | Meter Installations - Bl -SL |  | 2968 | 30684 | 4382 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
383 - House Regulators | 251383A | Regulators - Blanket - Flag |  | 0 | 7380 | 10663 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
383 - House Regulators | 252383A | Regulators - Blanket - King |  | 0 | 11242 | 14534 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
383 - House Regulators | 253383A | Regulators - Blanket - Pres |  | 0 | 14260 | 21356 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
383 - House Regulators | 255383A | Regulators - Blanket - Verde |  | 0 | 2763 | 6903 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
383 - House Regulators | 256383A | Regulators - Blanket - Nog |  | 0 | 943 | 1293 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
383 - House Regulators | 257383A | Regulators - Blanket - SL |  | 0 | 4069 | 2272 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 251384A | Regulator Install - Bl - Flag |  | 587 | 3908 | 9868 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 252384A | Regulator Install - Bl - King |  | 674 | 8796 | 10729 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 253384A | Regulator Install - Bl - Pres |  | 1337 | 19115 | 19720 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 255384A | Regulator Install- Bl - Verde |  | 1059 | 25634 | -7653 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 257384A | Regulator Install - Bl - SL |  | 460 | 18565 | -9037 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
384 - House Regulatory Installations | 256384A | Regulator Install - Bl - Nog |  | 0 | 2668 | -2193 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
385 - Industrial Measuring Regulating Station Equipment | 251385A | Industrial Metering - Flag |  | 2810 | 108354 | -75834 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
385 - Industrial Measuring Regulating Station Equipment | 253385A | Industrial Metering - Pres |  | 0 | 4524 | 41800 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
385 - Industrial Measuring Regulating Station Equipment | 255385A | Industrial Metering - Verde |  | 0 | 7905 | 8464 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
385 - Industrial Measuring Regulating Station Equipment | 257385A | Industrial Metering-Show Low |  | 0 | 0 | 17328 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
385 - Industrial Measuring Regulating Station Equipment | 252385A | Ind Meas & Reg Sta Eq-Bl- King |  | 20 | 3546 | 11096 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
387 - Other Equipment | 252387A | Other Distr Eq CP-Bl - King |  | 4825 | 74352 | -13001 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
387 - Other Equipment | 251387A | Other Distr Equip CP-Bl - Flag |  | 215 | -149 | 10346 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
387 - Other Equipment | 255387A | Other Distr Eq CP - Bl - Verde |  | 0 | 1786 | 1688 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
387 - Other Equipment | 253387A | Other Distr Equip CP-Bl-Pres |  | 297 | 19549 | -3467 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
387 - Other Equipment | 256387A | Other Distr Eq CP - Bl - Nog |  | 1166 | 71428 | -46584 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
387 - Other Equipment | 257387A | Other Distr Equip CP-Bl - SL |  | 1438 | 37483 | 9889 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
390 - Structures and Improvements | 253900A | Struct & Improv - New (Pres) |  | 28635 | 28635 | 48825 | 2026-06-01 | 12/31/2026 | REPLACE |  | 0 | Y
390 - Structures and Improvements | 255900A | Struct & Improv- New (Verde) |  | 0 | 0 | 26414 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
390 - Structures and Improvements | 253901A | UNSG Training Facility |  | 91307 | 97501 | -7253 | 2025-11-01 | 10/01/2026 | INSTALL |  | 0 | Y
390 - Structures and Improvements | 257900A | Structures & Improv-New SL |  | 5679 | 11617 | -5938 | 2026-05-01 | 2026-12-31 | REPLACE |  | 0 | Y
391 - Office Furniture and Equipment | 250912A | Comp Equip - UNSG |  | 0 | 38196 | 11522 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
391 - Office Furniture and Equipment | 250916A | Network IT Equip - UNSG |  | 0 | 17908 | 14092 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
391 - Office Furniture and Equipment | 250917A | Systems IT Equip - UNSG |  | 0 | 125411 | -99402 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
391 - Office Furniture and Equipment | 252910A | Office Furn & Equip-New (King) |  | 25471 | 26190 | 3870 | 2026-06-01 | 2026-12-31 | INSTALL |  | 0 | Y
391 - Office Furniture and Equipment | 253910A | Office Furn & Eq - New (Pres) |  | 0 | 2645 | 1105 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
392 - Transportation Equipment | 250000A | UNSG Transportation Equip |  | 534257 | 890957 | -236159 | 2026-06-01 | 12/31/2026 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 250940A | Tools,Shop,Gar Eq - New |  | 0 | 165151 | -147401 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 251940A | Tools,Shop,Gar Eq-New(Flag) |  | 0 | 15410 | -8410 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 252940A | Tool,Shop,Gar Eq-New (King) |  | 0 | 19912 | 8888 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 253940A | Tools,Shop,Gar Eq-New (Pres) |  | 0 | 35424 | 180 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 256940A | Tools,Shop,Gar Eq-New (Nog) |  | 0 | 0 | 15000 | 2026-10-01 | 2026-12-31 | INSTALL |  | 0 | Y
394 - Tool, Shop, and Garage Equip | 257940A | Tools,Shop,Gar Eq - New SL |  | 0 | 22780 | 17220 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
397 - Communication Equipment | 250970A | Comm Equip - New |  | 0 | 546 | 465888 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
397 - Communication Equipment | 257970A | Comm Equip- New SL |  | 0 | 4993 | 4467 | 2026-07-01 | 2026-12-31 | INSTALL |  | 0 | Y
397 - Communication Equipment | 250973A | UNSG Fixed Network Replacement |  | 85657 | 563738 | 1307737 | 2026-09-01 | 12/31/2026 | REPLACE |  | 0 | Y
397 - Communication Equipment | 251970A | Comm Equip - New (Flag) |  | 0 | 1584 | 1453 | 2026-07-01 | 2026-12-31 | REPLACE |  | 0 | Y
397 - Communication Equipment | 253970A | Comm Equip - New (Pres) |  | 6742 | 7343 | -4275 | 2026-06-01 | 2026-12-31 | REPLACE |  | 0 | Y
397 - Communication Equipment | 255970A | Comm Equip - New (Verde) |  | 0 | 0 | 1381 | 2026-10-01 | 2026-12-31 | REPLACE |  | 0 | Y
|  |  | 114190 | 1792604 | 5533947 | 5005039 |  |  |  | -466091 | -39174.72